## Title
Project Number |  | Title
|  | (Previous titles) | NA
Guide |  | Team
Stack | Framework
Programming Languages
Scripting Languages
Description
Objectives
Any Other Details

## Progress
Task Id | Task Name/Desc | Assigned To | Date of Review | Who | Completion Percent | Completion Status Desc (if needed) | Progress Report, Challenges, Work done | Review Comments
1 | Problem Identification |  |  | 45% |  |  | Progress Report : Defined the need for Quantum-Secure SFTP to counter post-quantum threats; aligned with defensive security applications.
1.1 | Primary Problem statement: This project proposes a Quantum Secure File Transfer Protocol (Q-SFTP) that enhances traditional SFTP by integrating post-quantum cryptographic algorithms to defend against quantum computing threats. The goal is to ensure future-proof, secure file transmission by maintaining confidentiality and integrity even in the presence of quantum-capable adversaries.​ | Team | Review 1 (17/03/2025) | CB.EN.U4CYS22008 CB.EN.U4CYS22026 CB.EN.U4CYS22028 CB.EN.U4CYS22030 | 100 | Completed
1.2 | Collect supporting evidence/Data & verfied the scope and boundaries of problem | Team | Review 1 (17/03/2025) | CB.EN.U4CYS22008 CB.EN.U4CYS22026 CB.EN.U4CYS22028 CB.EN.U4CYS22030 | 100 | Completed
2 | Task Planning
2.1 | 1) Collect PQC resources & testing targets 2) Set up development & test environment (lab) 3) Build the SFTP-like client & server (CLI prototype) | Team | Review 2 (08-07-2025) | CB.EN.U4CYS22008 CB.EN.U4CYS22026 CB.EN.U4CYS22028 CB.EN.U4CYS22030 | 100 | Completed all the respective prerequistie tasks | Progress Report: Created 8-month roadmap covering Design, Implementation, Testing, and Documentation. Assigned modules to members.
2.2 | For timeline the Gantt chart will be pasted in here
2.2.1
3 | Execution:
3.1 | 1) Collect PQC resources & safe testing targets - Complete 2) Integrate liboqs & implement Kyber + Dilithiums - inprogress 3) Implement Q-SFTP client (CLI)s- inprogress | Team | Review 3 (14/11/2025) | CB.EN.U4CYS22008 CB.EN.U4CYS22026 CB.EN.U4CYS22028 CB.EN.U4CYS22030 | 100 | Completed all the respective prerequistie tasks | Progress Report: PQC resources collected, liboqs Kyber/Dilithium demos run and basic Q-SFTP prototype built.
3.2
3.3
3.3.1
3.3.1.1
3.3.1.2
4 | Implementation
4.1 | 1) Integrate liboqs & PQ algorithms (Kyber + Dilithium) | 1-Jose Rohit | Review 4 (20/12/2025) | CB.EN.U4CYS22030 | 100 | Completed
4.1.1 | Design & implement PQ PKI + certificate flow | 2- Hemadhri | Review 4 (20/12/2025) | CB.EN.U4CYS22026 | 100 | Completed
4.1.2 | 3) Web Application User Interface | 3-Arul | Review 4 (20/12/2025) | CB.EN.U4CYS22008 | 100 | Completed
4.2 | 4) Functionalities{Login authentication,Remote File Browsing, file integrity verification, multi-file upload, setting upload speed, resumable file transfer, real-time progress updates } | 4-Hemanth | Review 4 (20/12/2025) | CB.EN.U4CYS22028 | 100 | Completed
4.3 | Implementation of Access Controls (RBAC) | Jose Rohit | Review 5 (12/1/2026) | CB.EN.U4CYS22030 | 100 | Completed
5 | User Interface Implementation | Hemanth | Review 5 (12/1/2026) | CB.EN.U4CYS22028 | 100 | Completed
5.1 | Hash Integration Verification | Hemadhri, Hemanth, Arul Sujith | Review 6 (21/1/2026) | CB.EN.U4CYS22026 CB.EN.U4CYS22028 CB.EN.U4CYS22008 | 100 | Completed
5.2 | Authentication of multiple users | Hemadhri, Arul Sujith, Jose Rohit | Review 6 (21/1/2026) | CB.EN.U4CYS22026 CB.EN.U4CYS22008 CB.EN.U4CYS22030 | 100 | Completed
5.3 | Shared Folder | Jose Rohit | Review 7(23/2/2026) | CB.EN.U4CYS22030 | 100 | Completed
5.4 | Docker Containerisation | Hemadhri, Hemanth Kumaar | Review 7(23/2/2026) | CB.EN.U4CYS22026 CB.EN.U4CYS22028 | 100 | Completed
5.5 | Blake2 Integration | Arul Sujith | Review 7(23/2/2026) | CB.EN.U4CYS22008 | 100 | Completed
5.6 | Project Report | Team | Review 7(23/2/2026) | CB.EN.U4CYS22008 CB.EN.U4CYS22026 CB.EN.U4CYS22028 CB.EN.U4CYS22030 | 100 | Completed
5.7 | Research Paper | Team | Review 7(23/2/2026) | CB.EN.U4CYS22008 CB.EN.U4CYS22026 CB.EN.U4CYS22028 CB.EN.U4CYS22030 | 20 | In progress
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation
5.6 | Docker Containerisation